## Tracking Sheet
WINDSOR PROJECT MANAGEMENT
S.No | Work | Contributors | Work done - Monday (2020/05/11) | Work done - Tuesday (2020/05/12) | Work done - Wednesday (2020/05/13) | Work done - Thursday (2020/05/14) | Work done - Friday (2020/05/15) | Issues/Blocking factors (if any) | Work Status
1 | Plugin & Integration | Mukesh | [7 empty] | In Progress
2 | 1. Plugin macro development and Integration 2. InfluxDB Query development for Data Normalization | Revathy | checking for outlier detection plan for server architecture (normalizations) | Learning Google Script Editor basics and method to include reference line in Chart. | [5 empty] | Done
3 | 1. Data Nomralization process 2. To respond for the query based on the SpreadSheet and time span. | Seenivasan | [7 empty] | None
4 | 1. Updating the NODE JS script in the API Server w.r.t. the changes updated by the Engineers. 2. Check and decide on the DB for Data Normalization. | Murugan
5 | 1. Working on Templates, Co-ordinate with Revathy for plugin changes. 2. Studying on Google sheets along with Prabhu. | Prabhu | Created Temlpate for Example 3 and resp. Userforms | Worked in Spreadsheet Plugins | Worked in Spreadsheet Plugins. Worked in Templates and also tried to add a date picker in the VBA code.
6 | Review the changes | Vel
7 | 1. Looking on Google sheet along with Prabhu, How to create scripts for exporting Data from server. 2. To improve the security between App container and plugin connection 3. Support team if any help required on communicate b/w App container and plugin connection via http request | Sivaprakash